## READ ME
Risk Template
Revision Date: | 2021-08-23
Last Edit Date: | mm/dd/yyyy
Team Name:
DAQ Cycle:
Instructions:
Risk List sheet:
The ID and Title of the risk must first be specified. The Condition, Departure, Asset, and Concequence should be specified and the Statement will be automatically generated. The Severity categories including Safety, Technical, Cost, and Schedule must be ranked from 1 to 5. The detailed explanations of the categories and their ratings are described in the "Descriptions" sheet. The risk Likelihood can be ranked from 1 to 5 from a drop-down menu. Criticality and Position will be automatically calculated basd on the specified Severity and Likelihood rankings. The Status and Handling of a risk must be specified from a drop-down menu. The "Descriptions" sheet includes all explanations needed to input and select all of these specifications. The Current Handling Strategy must also be specified.
Criticality Matrix sheet:
This sheet includes a Criticality Matrix which is populated based on Likelihood and Consequence.
Descriptions sheet:
This sheet includes the Likelihood Score Table, Severity Score Table, Handling Description, and Status Description. These tables must be referenced when populating the table in the "Risk List" sheet.

## Risk Guidance
| When developing proper risks there are a couple items to keep in-mind: | Guiding Question
1 | A good risk has a connection to the implemented or intended design of a system. Risks are outcomes from a design decision which has been made at the time of the risk assessment. If a consideration must be designed around, those are not a risk until the design demonstrates that it does not address those considerations. An example of this is structural fatigue. All spacecraft parts must be designed to withstand the launch and orbit environment. The source of risk is not that a known fatigue case will occur, it is if the current design will undergo a failure given that fatigue case. Another source of risk could be uncertainty in the assumed environment, such that current assumptions in design may not meet the real environment. For this risk, the impact may not be failure, but an increase in mass and volume to account for change in the design with new information. In either case the design could undergo a a change and/or failure that is a risk to the project and which should be tracked to determine what any actions to be taken. | What decision in the known design is causing the risk?
2 | Sources of risk can and should include uncertainty in our understanding of the design as it applies to its performance in meeting requirements. An example of this is in the selection of a sensor with a narrow detection range which is dependent on the assumed input. Here the risk might be that our understanding of the input is not well understood and if the expected range is exceeded then the sensor cannot function (which impacts the mission by a loss of function no longer meeting a requirement). Another example would be an experimental heat strap, whose heat conduction is based on theorized performance. In this case the theorized performance of the unit may not be realistic, thus the heat strap may be unable to remove the heat it needs when implemented. The risk in this case is in the uncertainty in the performance of the heat strap with a possible consequence of thermal ranges being exceeded during operation (failure to meet a requirement of thermal control). When constructing a risk of this type, the source that drives the risks should be clear, not vague general considerations. | What about the design are we unsure of that impacts its performance and final implementation?
3 | Consequence is a property of a risk, not the risk itself. Risks should have each core element clearly understood (Condition, Departure, Asset, Consequence). | What is the source that results in the risk's consequence?
4 | Risk must have an impact and source that is known to a level where likelihood and consequence ratings can be applied (even if it is an informed guess). If you can not apply some motivated value of likelihood and consequence to SMEs, then you should work on better representing the risk. | Do we understand what causes the risk's consequence?
5 | Risks exist in the development and management of the system. Same idea applies as in the prior points. A risk must be a clear result of a management or development approach, or uncertainty in the assumptions used for management and development (e.g., labor, costs, etc.). | What in the development or leadership approach could be a risk?
6 | Risks do not exist for a design which has yet to be defined. Without some design in place, an assessment of likelihood and consequence cannot be effectively considered. Risks should be considered in the trade and selection process, but these are not long-term risks that must be tracked. Only risks inherent to the current design are tracked in this sheet. | What is our current design that which we can determine the risk consequence from?

## Risk List
[7 empty] | Pre-handling | [5 empty] | Handling Method |  | Post-handling
ID | Title | Condition | Departure | Asset | Consequence | Statement | Severity |  |  |  | Likelihood | Criticality | Handling | Handling Strategy | Severity |  |  |  | Likelihood | Criticality | Positon | Status | Revision Date [mm/dd/yyyy] | Revision Notes
[7 empty] | Safety | Performance | Cost | Schedule |  |  |  |  | Safety | Performance | Cost | Schedule
1 | Risk Name | [Condition] | [Departure] | [Asset] | [Consequence] | Given that [Condition], there is a possibility of [Departure] adversely impacting [Asset], which can result in [Consequence]. | 1 | 5 | 1 | 1 | 3 | 15 | Research | TBD or current description of handling strategy. | 1 | 1 | 1 | 1 | 5 | 5 | 125 | Open |  | TBD or current description of handling strategy.
Note on I3: See the descriptions sheet for defintions.
Note on Q3: See the descriptions sheet for defintions.

## Criticality Matrix
Risk Criticality Matrix
5 | SEVERITY
4
3
2
1 | [5 empty] | 1
LIKELIHOOD
|  | 1 | 2 | 3 | 4 | 5

## Descriptions
Likelihood Score Table
Level | Likelihood of Occurrence (p) | p Value Range
5 | Near certainty | p > 80%
4 | Highly likely | 60% < p ≤ 80%
3 | Likely | 30% < p ≤ 60%
2 | Low likelihood | 5% < p ≤ 30%
1 | Not likely | p ≤ 5%
Severity Score Table
Level | 1 | 2 | 3 | 4 | 5
Performance | Minimal consequence | Minor consequence | Unable to achieve objective/goal, but greater than minimum success | Unable to achieve multiple objectives/goals, but minimum success can be claimed | Unable to achieve minimum success on objectives/goals
Safety | Minimal consequence | Minor consequence | Minor consequence, damage to asset but repairable | Major consequence, substantial damage to asset | Destroyed, asset is un-repairable, total loss
Schedule | Minimal consequence | Critical path is not slipped, < 10-day impact to tasks | Possible impact slipped tasks to critical path | Critical path slips | Critical path slips and one or more milestones cannot be met
Cost | Minimal consequence | Minor cost impact, cost variance < 5% expected value | Cost impact > 5% but < 10% of expected value | Cost impact > 10% but < 15% of expected value | Major cost impact with cost > 15% of expected value
Handling | Description
Accept | Risks in which the impacts (consequences) are tolerable should the risk be realized. Accepted risks will be reviewed periodically to ensure conditions/assumptions have not changed requiring the risk to be “reopened”.
Mitigate | Risks whose likelihood of consequence will be reduced by taking proactive steps
Research | Risks that need more information/analysis before a decision can be made to mitigate or accept (a future reassessment date needs to be specified to determine further action).
Watch | Risks in which the impacts (consequences) are tolerable should the risk be realized, given the current environment / circumstances. But the impacts may be intolerable if the current environment / circumstances change. However, risks with a handling strategy of “Watch” must be reviewed on a clearly defined and regular basis.
Status | Description
Open | Risk has been identifed and needs to be addressed.
Closed | Closed risks will no longer be actively mitigated or monitored. Either the risk is deemed unneeded anymore or the risk has been reduced to a level where the remaining risk is considered negligible and further risk reduction activity is deemed unnecessary may be closed. Closed risks should be re-evaluated if new knowledge is gained that may require the risk to be re-opened or a new risk generated.